## Roles
Roles | Responsibility (RACI) | Individual/Organization | Contact Information
Sponsoring Entities | Hosting and marketing the project (consult & inform) | TBD - - - The Autism Societies of Central Virginia, Northern Virginia, and Tidewater Virginia | Email: ann.flippin@ascv.org Mail: Autism Society of Central Virginia 8730 Stony Point Pkwy, Ste 150 Richmond, VA 23235
Sponsor also known as: Citizen Sponsor, Authorized Representative, Requestor, Consultant, Constituent | Sole contact for all verbal and written communications during the plate development process - may delegate Sponsor's responsibilities to Advocate (accountable) | Ryan James, Operations Director (Ann Flippin, ASCV Executive Director) | Email: ryan.james@ascv.org
Advocate (not a real role) | Coordinate project tasks, manage scheduling and reminders, and ensure effective communication throughout all phases of the project - may perform Sponsor's responsibilities with oversight (responsible) | Anna Mooney, Va-LEND Student | Email: grlofgd@yahoo.com
Legislator (aka VA Legislative Sponsor) | Sponsors the new license plate for legislation (inform) | Del. Betsy Carr (D) - House District 78 (Richmond) https://www.betsycarr.org/ | email: DelBCarr@house.virginia.gov Mail: P.O. Box 406 Richmond, Virginia 23218 General Assembly Building, Room 1110 201 North 9th Street Richmond, Virginia 23219 (804) 698-1078
DMV License Plate Development (LPD) Office | (inform) | Carolyn Wade-Easley License Plate Development | Email: PlateDevelopment@dmv.virginia.gov carolyn.easley@dmv.virginia.gov (804) 367-0368 Mail: Virginia Department of Motor Vehicles License Plate Development, Room 322 Post Office Box 27412 Richmond, VA 23269-00011 FAX: 804-367-6379
Lobbyist | Assist with creation of the bill and communication with the legislator (inform, responsible) | Two Capitols Consulting Devon Cabot Randy Pearson | Email: devon@2capconsulting.com randy@2capconsulting.com Mail: 1205 E. Main St. #1E Richmond, VA 23219 https://www.2capconsulting.com
Marketer | Approve the preliminary plate design, build the webpage and pre-order functionality, oversee all marketing efforts and materials (responsible) | Matt Gordon, ASCV Marketing
Stakeholders | (inform) | ASCV Board, Autism Community

## Tasks
Objective | Task | Responsible | Status | Resources (links) | Start | Due | Notes/Updates
Understand Plate Process | Review "Special Interest Groups and Military Sponsor Information" | Advocate | Completed | Special Interest Groups and Military Sponsor Information | 2024-10-01 | 2024-10-01 | Special Plate VA Code
Understand Plate Process | Identify another non-profit that has gone through this process | Advocate | Completed | CBS 6 News article - Celebrate Diversity 2025 License Plate | 2024-10-01 | 2024-10-01 | VCU new plate FAQ & application
Retire Unlocking Autism | Request (email) DMV to discontinue/retire "Unlocking Autism" plate | Advocate | Completed | EMail - Request to Discontinue Unlocking Autism License Plate.pdf | 2024-10-07 | 2024-10-07
Understand Plate Process | Email another non-profit that has gone through this process | Advocate | Completed | Email - Seeking Guidance on New License Plate Initiative.pdf | 2024-10-07 | 2024-10-07
Create License Plate Design | Establish license plate name & gain approval from Sponsor | Advocate | Completed |  | 2024-10-03 | 2024-10-14 | Suggested name: Autism Acceptance
Understand Plate Process | Check-In Meeting | Advocate | Completed | Meeting Notes | 2024-10-22 | 2024-10-22 | Agenda: Review project Discuss first iteration of plate designs Plan next steps
Understand Plate Process | Seek advice from (meet with) another non-profit that went through the process | Advocate | Completed | Meeting Notes | 2024-10-07 | 2024-10-22 | Diversity Richmond New Plate FAQ & application
Retire Unlocking Autism | Reach out to contact name given by DMV to request retiring "Unlock Autism" | Advocate | Completed | Email - Request Unlocking Autism to be Retired.docx | 2024-10-22 | 2024-10-25 | Email sent 10/24 using webportal https://www.unlockingautism.org/
Secure Legislator | Identify a legislator | Sponsor | Completed |  | 2024-10-03 | 2024-10-25 | Delegate Betsy Carr
Create License Plate Design | Create preliminary plate design | Advocate | Completed | AutismAwarenessPlateDesigns.pdf | 2024-10-03 | 2024-10-30 | Draft of plate design ideas shared
Understand Plate Process | Check-In Meeting | Advocate | Completed | Meeting Notes | 2024-10-30 | 2024-10-30 | Agenda: Review any updates Share name of Legislator Share affiliate agreement and updates Discuss second iteration of plate designs
Secure Legislator | Contact legislator and secure his/her support | Lobbyist (Legislator) | Completed | Email - Confirmed Del Carr as Legislator.pdf | 2024-10-11 | 2024-11-01
Modify ASCV Website | Create a wireframe for the webpage | Advocate | Completed | WebsiteWireframe.pptx | 2024-11-04 | 2024-11-20 | previous: ASCV's FAQ & application
Connect with other Autism Societies | Create affiliate agreement | Sponsor | In Progress |  | 2024-10-21 | 2024-12-03
Create License Plate Design | Gain plate design insight from ASCV Marketer | Sponsor | Completed |  | 2024-12-03 | 2024-12-03
Understand Plate Process | Check-In Meeting | Sponsor | Completed | Meeting Notes | 2024-12-03 | 2024-12-03 | Agenda: Review any updates Share affiliate agreement and updates Discuss Matt's insights on plate designs Share website requirements progress
Create License Plate Design | Modify plate design based on Marketer's feedback | Marketer | Completed |  | 2024-12-03 | 2024-12-06
Marketing Campaign | Write FAQ and instructions based on DMV's FAQ and using other organizations as an example | Marketer | Not Started | charitable tax deduction FAQs | 2024-11-20 | 2024-12-06 | example: VCU new plate FAQ & application
Create License Plate Design | Gain plate design approval from ASCV Marketer | Sponsor | Completed |  | 2024-12-06 | 2024-12-10
Secure Legislator | Prefill in form VSA 155 | Sponsor | Completed | Legislator Acknowledgment - VAS 155 | 2024-12-03 | 2024-12-10
Secure Legislator | Send form VSA 155 and preliminary design to Lobbyist to gain Legislator signature | Sponsor | In Progress |  | 2024-12-10 | 2024-12-10 | Name and preliminary design must be completed first
Modify ASCV Website | Figure out a way to handle online pre orders (money & form submission) | Marketer | Not Started | previous: ASCV's FAQ & application | 2024-12-02 | 2024-12-13
Secure Legislator | Complete form VSA 154 | Sponsor | In Progress | Plate Sponsor - VAS 154 | 2024-12-16 | 2024-12-16
Connect with other Autism Societies | Email other autism societies to inform of initiative & attach affiliate agreement | Sponsor | Not Started |  | 2024-11-18 | 2024-12-17
Connect with other Autism Societies | Set up communication cadence | Marketer | Not Started |  | 2024-11-18 | 2024-12-17
Marketing Campaign | Meet with Marketer to identify marketing tasks | Marketer | Not Started |  | 2024-12-16 | 2024-12-20
Marketing Campaign | Add marketing tasks to the planner | Marketer | Cancelled |  | 2024-12-20 | 2024-12-20
Modify ASCV Website | Update the webpage with the components with an iteration approach | Marketer | Not Started |  | 2024-12-02 | 2024-12-31
Retire Unlocking Autism | Placeholder - communications with Unlocking Autism in Baton Rouge, LA to retire plate | Sponsor | In Progress | Email - Unlocking Autism Contact.pdf | 2024-10-28 | 2024-12-31 | Recent previous correspondence to info@unlockingautism.org on 11/4/24 and 12/2/24 - found a contact who forwarded the email to the organization's founder
Modify ASCV Website | Website go live | Marketer | Not Started |  | 2024-12-30 | 2025-01-03
Marketing Campaign | Create life size mockup of plate design | Marketer | Not Started |  | 2025-01-06 | 2025-01-17
Modify ASCV Website | Create a webpage based on the wireframe with placeholders | Marketer | Not Started |  | 2025-01-06 | 2025-01-17
Report Pre-orders | Complete & send form VSA 10D to DMV (eom) | Sponsor | Not Started | Preorder Request Sponsor Guidelines (2017) - VSA 10D | 2025-01-01 | 2025-01-31 | DMV to send VSA 10D 3 days after receiving forms 154 & 155
Secure Legislator | Receive form VSA 155 back from Legislator and send to Sponsor | Lobbyist (Legislator) | Not Started |  | 2024-12-10 | 2025-01-31
Secure Legislator | Send forms VSA 154 & 155 to DMV | Sponsor | Not Started |  | 2025-01-31 | 2025-01-31 | 2025-01-31 | DMV to send VSA 10D 3 days after receiving forms 154 & 155
Secure Legislator | Visit General Assembly - meet representing legislator | Sponsor | Cancelled |  | 2025-01-31 | 2025-01-31
Report Pre-orders | Complete & send form VSA 10D to DMV (eom) | Sponsor | Not Started |  | 2025-02-01 | 2025-02-28
Report Pre-orders | Complete & send form VSA 10D to DMV (eom) | Sponsor | Not Started |  | 2025-03-01 | 2025-03-31
Report Pre-orders | Complete & send form VSA 10D to DMV (eom) | Sponsor | Not Started |  | 2025-04-01 | 2025-04-30
Report Pre-orders | Complete & send form VSA 10D to DMV (eom) | Sponsor | Not Started |  | 2025-05-01 | 2025-05-31
Report Pre-orders | Complete & send form VSA 10D to DMV (eom) | Sponsor | Not Started |  | 2025-06-01 | 2025-06-30
Report Pre-orders | Complete & send form VSA 10D to DMV (eom) | Sponsor | Not Started |  | 2025-07-01 | 2025-07-31
Report Pre-orders | Complete & send form VSA 10D to DMV (eom) | Sponsor | Not Started |  | 2025-08-01 | 2025-08-31
Report Pre-orders | Complete & send form VSA 10D to DMV (eom) | Sponsor | Not Started |  | 2025-09-01 | 2025-09-30
Report Pre-orders | Complete & send form VSA 10D to DMV (eom) | Sponsor | Not Started |  | 2025-10-01 | 2025-10-31
Report Pre-orders | Complete & send form VSA 10D to DMV (eom) | Sponsor | Not Started |  | 2025-11-01 | 2025-11-30
Create License Plate Design | Sign & email "License Plate Design Release Agreement" to DMV | Sponsor | Not Started | License Plate Design Release Agreement | 2025-12-31 | 2025-12-31 | Owner/Designer of the plate design will need to sign this document
Report Pre-orders | Send form VSA 10D to DMV (eom) | Sponsor | Not Started |  | 2025-12-01 | 2025-12-31
Report Pre-orders | Verify 450 pre orders have been received with legislator | Sponsor | Not Started |  | 2025-12-01 | 2026-01-15
Connect with other Autism Societies | Visit General Assembly - attend Autism Advocacy Day - promote bill | Sponsor | Not Started |  | 2026-01-30 | 2026-01-30
Report Pre-orders | Send form VSA 10D to DMV (eom) | Sponsor | Not Started |  | 2026-01-01 | 2026-01-31
Report Pre-orders | Finalize all documentation (logo use agreement & plate design) with DMV | Sponsor | Not Started |  | 2026-07-15 | 2026-08-31
Report Pre-orders | Approve metal prototype | Sponsor | Not Started |  | 2026-11-11 | 2026-11-15